## Slide 1
ANNUAL ACTION PLAN : FY 22-23
Program | Projects | Nature of Project | Schedule 7 alignment | Mode of implementation | Location | Budget from FY 22-23 allocation (Rs. In Lakhs)
Employability | Vocational skill training (Training in relevant skills and employment of at least 75% of beneficiaries): Swayam Health 22-23 | Short term | Point ii | Through an implementing agency (RPGF) | Pune | 8
Total |  |  |  |  |  | 8
Note: All figures are in Rs. Lakhs.
In all 65 women candidates planned to be trained in in “General Duty Assistant” training and soft skills
Swayam Health is a program which equips women/girls to have careers in the healthcare sector.
Trained beneficiaries are provided employment avenues with hospitals, home-based healthcare agencies or diagnostic centers.

## Slide 2
PROJECT TIMELINE & DISBURSEMENT OF FUNDS
Sr. No | Program Stage | Oct-22 | Nov-23 | Dec-22 | Jan-23 | Feb-23
1 | Mobilization | 100 |  |  |  | 
2 | Enrollment | 65 |  |  |  | 
3 | Classroom Training completion |  | 65 |  |  | 
4 | Practical training completion |  |  | 65 |  | 
5 | On-job-training Completion |  |  |  | 65 | 
6 | Assessment completion |  |  |  | 65 | 
7 | Certification |  |  |  | 65 | 
8 | Placements completion |  |  |  |  | 65
Nos in the table refer to no of candidates
Project would be initiated in October and will be completed by Feb’23
In all 65 candidates would be trained and approx. 75% would be supported with employment
Disbursement schedule(Amt in lakhs) |  | 
Amount | Month | % of request
4,00,000 | October 2022 | 50%
4,00,000 | December 2022 | 50%